IdeaVault

DEVELOPMENT ROADMAP
AND IMPLEMENTATION STRATEGY

Yuva Intern — Week 3 Task

| Document detail | Value |
| --- | --- |
| Project | IdeaVault — personal idea-management application |
| Prepared by | Shreya Gupta |
| Version | 1.0 |
| Date | 14 October 2026 |
| Source baseline | Week 1 Software Requirements Document (Version 1.0) and Week 2 System Architecture Design (Version 1.0) |
| Document status | Proposed roadmap for review; not a claim of implementation or testing |

Capture ideas. Connect thinking. Turn plans into action.

# Document Control

| Version | Date | Change summary |
| --- | --- | --- |
| 1.0 | 14 October 2026 | Initial Week 3 development roadmap, milestones, implementation approach, resource estimate, testing and risk plan. |

This document translates the approved-direction requirements and proposed architecture into a practical build sequence. The platform and exact storage technology remain open decisions carried forward from Weeks 1 and 2.

# Executive Summary

IdeaVault is planned as a lightweight, single-user, local-first application for capturing, organising, searching, and progressing personal ideas. This roadmap proposes a staged implementation that begins with scope confirmation and screen design, then establishes the domain model and validation rules, implements local persistence and core idea management, adds organisation and dashboard features, and finishes with integration, acceptance testing, and release preparation.

A small, iterative Agile approach is recommended because it allows the core workflow to be demonstrated early and feedback to be incorporated before optional features are completed. The initial effort estimate is approximately 33 hours, consistent with the Week 1 planning estimate. This is a planning estimate, not a guarantee.

# 1. Purpose, Objectives, and Scope

## 1.1 Purpose

The purpose of this roadmap is to define development phases, deliverables, milestones, dependencies, resource needs, implementation practices, integration steps, and test gates for the first IdeaVault prototype.

## 1.2 Development objectives

Deliver the Must-priority requirements before optional enhancements.

Keep presentation, business logic, repository/data access, and local persistence separate, as proposed in the Week 2 architecture.

Preserve idea data on the same device after normal closure and reopening.

Provide clear validation, empty states, delete confirmation, and storage-error feedback.

Use requirement-linked tests to verify core behaviour and data integrity.

Keep the first release local-first and single-user; do not introduce cloud sync, accounts, AI, social features, or payments.

## 1.3 Scope baseline

| Included in Version 1 | Excluded from Version 1 |
| --- | --- |
| Create, view, edit, and delete ideas; required title; optional description and metadata; statuses; tags; search; filters; favourites; sorting; dashboard counts; local persistence; validation and clear feedback. | AI-generated ideas or summaries; cloud synchronisation; user accounts; collaboration/social feeds; attachments/audio import; payments; ads; marketplace features; guaranteed originality or legal checks. |

# 2. Implementation Methodology

## 2.1 Recommended approach: Agile, small iterations

Use short, focused iterations with a working outcome at the end of each phase. Review the result against the relevant requirements and acceptance criteria before proceeding. This is appropriate for a beginner-sized prototype because platform choices and some product decisions remain open, and early testing can expose misunderstandings before they spread.

| Practice | How it will be used |
| --- | --- |
| Backlog prioritisation | Keep Must requirements first; schedule Should requirements after the essential create/read/update/delete and persistence flow works. |
| Iteration planning | Choose a small set of tasks, define the expected result, and identify dependencies before coding. |
| Definition of done | Code is integrated, relevant tests pass, errors are handled, and the requirement/test evidence is recorded. |
| Review | Demonstrate the phase outcome and record defects or decisions that need attention. |
| Change control | Assess new ideas against Version 1 scope; defer out-of-scope requests rather than expanding the MVP. |

## 2.2 Development workflow

Confirm the web-versus-Android platform and sketch the four principal screens: Dashboard, Idea List, New/Edit Idea, and Idea Details.

Define the Idea data model, unique ID behaviour, supported status and priority values, and title validation.

Implement a repository interface and a platform-appropriate local storage adapter.

Build core idea-management operations and connect them to the screens.

Add search, filters, tags, status changes, favourites, sorting, and dashboard summaries.

Run unit, repository integration, UI, acceptance, and performance checks; fix and retest defects.

Prepare a release candidate, document limitations, and provide a short walkthrough.

# 3. Development Roadmap and Schedule

The schedule below is a proposed sequence. Estimates total 33 hours, matching the Week 1 baseline. Calendar dates should be assigned after the platform decision and available working hours are confirmed.

| Phase | Effort | Main activities | Milestone / exit condition |
| --- | --- | --- | --- |
| 1. Scope and platform confirmation | 3 h | Review Week 1 and Week 2 documents; choose web or Android; confirm open decisions and MVP backlog. | Approved platform, screen flow, and prioritised backlog. |
| 2. UI wireframes and domain model | 4 h | Sketch Dashboard, Idea List, New/Edit, and Details; define Idea fields, enums, IDs, and validation rules. | Wireframes and documented data model. |
| 3. Validation and core service | 4 h | Implement title validation, supported status/priority values, defaults, timestamps, and create/read/update/delete use cases. | Core rules and service tests pass. |
| 4. Repository and local persistence | 5 h | Create repository contract and local storage adapter; verify create/read/update/delete and restart persistence. | Data survives normal close/reopen; storage errors are handled. |
| 5. Core screens and workflows | 6 h | Connect screens to business logic; implement idea list/details, new/edit, delete confirmation, and user feedback. | Core workflow is usable; AT-01, AT-02, AT-03, AT-07, AT-08 are checked. |
| 6. Organisation and dashboard | 5 h | Add search, filters, tags, status/favourite controls, sorting, empty states, and status counts. | Relevant search/filter/status and dashboard tests pass. |
| 7. Integration, quality, and release preparation | 6 h | Run acceptance and performance checks; review accessibility/privacy; fix defects; prepare documentation and demo. | Release checklist completed; known limitations documented. |

## 3.1 Milestone gates

| Gate | Decision / evidence required |
| --- | --- |
| G1 — Plan approved | Platform selected; Version 1 scope and screen flow confirmed. |
| G2 — Rules ready | Idea schema, unique ID approach, title validation, and allowed values documented and tested. |
| G3 — Persistence ready | Repository operations work; data persists after normal restart; failure paths are checked. |
| G4 — Core workflow ready | Create, view, edit, and delete work with clear feedback and delete confirmation. |
| G5 — Feature complete | Search, filters, tags, status, favourites, sorting, and dashboard summary work as prioritised. |
| G6 — Release candidate | Acceptance tests reviewed, critical defects resolved, performance target checked, and limitations recorded. |

# 4. Resource and Effort Estimation

The project is scoped for a junior developer or small student team. The main resource is development time; a modern browser or Android test device, an editor, and a version-control tool are sufficient for the proposed prototype.

| Resource | Purpose | Planning note |
| --- | --- | --- |
| Developer time — 33 hours | Design, implementation, integration, testing, and documentation. | Estimate only; allow additional time if the platform or storage choice creates unexpected work. |
| Computer and target device | Build and test a phone-sized web view or Android-sized interface. | Confirm the target platform before selecting implementation details. |
| Code editor and runtime/tooling | Write, run, debug, and test code. | Use familiar, lightweight tools; avoid unnecessary frameworks. |
| Version control (recommended) | Track changes and recover from regressions. | Git and a repository host are optional; the app must not depend on hosting at runtime. |
| Test dataset | Verify search, filters, sorting, and performance. | Use representative sample ideas, including a 1,000-idea collection for the proposed performance check. |

# 5. Integration Strategy

Integrate from the domain and data boundaries outward. The user interface must not write directly to storage; it should call application use cases, which use the repository interface and local storage adapter.

| Integration step | Approach | Verification |
| --- | --- | --- |
| 1. Domain and validation | Define the Idea record, unique ID, status/priority values, and validation before UI integration. | Unit tests for blank title, supported values, and data defaults. |
| 2. Repository and storage | Connect repository operations to the selected local storage technology. | Create/read/update/delete tests and close/reopen persistence test. |
| 3. Core service and screens | Connect New/Edit, List, and Details screens to service methods. | Create, edit, view, and confirmed delete flows. |
| 4. Organisation features | Connect search/filter/sort and tag/status/favourite operations to the same data source. | Verify result consistency across list and dashboard. |
| 5. Dashboard and shared states | Calculate summary counts from saved records; reuse error and empty-state patterns. | Counts match records; empty and failure states provide useful actions. |
| 6. Full-system regression | Run the complete acceptance set after integrations and fixes. | Re-run affected tests after each fix; record pass/fail and defects. |

# 6. Testing and Quality Assurance Plan

Testing is planned evidence gathering, not a statement that the application has already passed. Results should be recorded during implementation.

| Test level | Focus | Examples / expected result |
| --- | --- | --- |
| Unit tests | Business rules in isolation. | Blank title rejected; supported status/priority values accepted; tag normalisation and sorting behave consistently. |
| Repository integration | Data access and persistence. | Records are created, read, updated, and deleted by unique ID; data remains after normal restart; storage failures are surfaced. |
| UI tests | Screen feedback and navigation. | Validation message appears; delete confirmation is required; empty states and status/favourite controls are clear. |
| Acceptance tests | Week 1 acceptance criteria AT-01 to AT-10. | Create, blank-title rejection, edit, search, status filter, status change, delete confirmation, persistence, empty state, optional fields. |
| Performance check | Proposed target from Week 1. | With 1,000 sample ideas, list opening and simple search should normally complete within 2 seconds on a typical supported device. |
| Accessibility and privacy review | Readable text, labelled controls, status not conveyed by colour alone, local-only data boundary. | Review screen labels and feedback; verify no external transmission is introduced in Version 1. |

## 6.1 Defect severity and handling

| Severity | Example | Response |
| --- | --- | --- |
| Critical | Saved ideas are lost, corrupted, or one idea overwrites another. | Stop release preparation; reproduce, fix, and rerun data-integrity and persistence tests. |
| High | A core Must workflow such as create, edit, search, or delete is unusable. | Prioritise correction before proceeding to release candidate. |
| Medium | A Should feature or secondary screen behaves incorrectly. | Fix within the remaining scope/time or document as a known issue if non-blocking. |
| Low | Minor visual inconsistency that does not prevent use. | Record and correct if time permits; do not compromise core reliability. |

# 7. Risk Assessment and Mitigation

| Risk | Initial level | Possible impact | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| R-01 Feature creep | Medium | Optional requests expand the MVP and delay core features. | Use the Week 1 scope baseline; Must requirements first; defer AI, sync, collaboration, and other excluded items. | Project owner / developer |
| R-02 Platform remains undecided | Medium | UI and storage decisions cannot be finalised. | Resolve web vs Android in Phase 1 before implementation-specific work. | Project owner |
| R-03 Local data loss | Medium | Cleared browser/app data or device loss may remove ideas. | Test persistence and report storage errors; clearly explain local-only storage; consider export/backup only as a separately approved enhancement. | Developer |
| R-04 Data integrity defect | High | An edit targets the wrong idea or overwrites a record. | Use unique IDs rather than list position; test update/delete against multiple records. | Developer |
| R-05 Search or performance shortfall | Medium | Users cannot find ideas quickly or the 2-second target is missed. | Test representative data including 1,000 ideas; review query logic and indexing where appropriate. | Developer / tester |
| R-06 Inconsistent status values | Medium | Dashboard counts and filters disagree. | Use one shared status definition in UI, logic, storage, and tests. | Developer |
| R-07 Storage failure is hidden | Medium | UI reports success when saving failed. | Return explicit success/failure outcomes; show an actionable message and preserve entered form data where practical. | Developer |
| R-08 Privacy expectation mismatch | Low–Medium | Users assume cloud backup or synchronisation exists. | State that Version 1 is local-only and does not transmit idea content to external services. | Project owner / developer |
| R-09 Insufficient testing time | Medium | Defects remain near the deadline. | Reserve the final six hours for integration, acceptance, quality review, and fixes; prioritise core acceptance tests. | Developer |

# 8. Dependencies and Open Decisions

The roadmap depends on the following decisions carried forward from Weeks 1 and 2. They should be resolved before the affected implementation begins.

Platform: web prototype or Android prototype.

Local storage technology appropriate to the chosen platform.

Tag behaviour: free-form labels, reuse existing tags, or both.

Whether export-to-file/backup is deferred; it is not included in the current Version 1 baseline.

Target-date behaviour: informational only in Version 1; reminders are not promised.

Supported browser/device and accessibility checks to be used for review.

# 9. Deployment and Release Strategy

Deployment is a proposed final activity after the release candidate passes the agreed checks. The exact deployment route depends on the platform selected in Phase 1.

| Stage | Action | Release condition |
| --- | --- | --- |
| Build preparation | Create a clean runnable build and verify the selected target environment. | Application opens without blocking errors. |
| Configuration review | Confirm local storage configuration and remove unnecessary external-service dependencies. | Version 1 remains local-first; no cloud account or sync dependency. |
| Smoke test | Run a short end-to-end check: create idea, edit, search, change status, delete after confirmation, restart. | Core workflow behaves as expected. |
| Release notes | Document features, limitations, platform support, and local-data caveat. | No claim of backup, sync, reminders, or untested behaviour. |
| Demo and handover | Show main screens, explain architecture and test evidence, list known issues and future candidates. | Reviewer can understand scope, results, and remaining decisions. |

# 10. Definition of Done

The feature maps to a Week 1 requirement or an explicitly approved implementation task.

Business rules are kept out of screen event handlers where practical and use the planned module boundaries.

Validation and failure cases provide clear user feedback; the interface does not show false success.

Relevant unit, integration, UI, or acceptance tests have been run and their results recorded.

Data updates use unique IDs and do not depend on list position.

No out-of-scope network, account, AI, payment, or collaboration feature has been added.

Known limitations and any uncompleted tests are documented honestly.

# 11. Deliverables and Reporting

| Deliverable | Contents / evidence |
| --- | --- |
| Roadmap and backlog | Phases, estimates, dependencies, priorities, and milestone gates. |
| Wireframes and domain model | Four principal screens and the Idea record fields/enums. |
| Implementation | Core service, repository, local persistence, screens, and organisation features as prioritised. |
| Test evidence | Test cases, pass/fail results, defects, fixes, and retest outcomes. |
| Release package / demo | Runnable prototype for the selected platform, short walkthrough, limitations, and future recommendations. |

# 12. Public References

These references are carried forward from the Week 1 and Week 2 documents and provide background for requirements engineering, web storage, and application security. This roadmap does not claim formal certification or full compliance.

ISO/IEC/IEEE 29148:2018 — Systems and software engineering: Life cycle processes — Requirements engineering. https://www.iso.org/standard/72089.html

ISO Online Browsing Platform — public preview and terminology for ISO/IEC/IEEE 29148. https://www.iso.org/obp/ui/

OWASP Application Security Verification Standard — security verification concepts for software applications. https://owasp.org/www-project-application-security-verification-standard/

MDN Web Docs — IndexedDB API (background for the optional browser prototype storage recommendation). https://developer.mozilla.org/en-US/docs/Web/API/IndexedDB_API

# 13. Conclusion

This roadmap provides a feasible, staged plan for moving IdeaVault from requirements and architecture into implementation. It prioritises the core idea-management workflow, keeps the proposed layered architecture intact, and places local persistence, data integrity, clear error handling, and requirement-linked testing at the centre of delivery. The total estimated effort is 33 hours. Before coding begins, the target platform and remaining open decisions should be confirmed; implementation and test results must then be recorded as work is completed.

# Appendix A — Requirement-to-Phase Traceability

| Requirement group | Planned phase(s) | Verification evidence |
| --- | --- | --- |
| FR-01–FR-06: idea CRUD and validation | Phases 3–5 | Unit tests; AT-01, AT-02, AT-03, AT-07. |
| FR-07–FR-09: search, filters, tags | Phase 6 | AT-04, AT-05 and feature-specific tag/filter checks. |
| FR-10–FR-12: status, next action, favourites | Phases 5–6 | Status and favourite tests; verify optional next-action fields save correctly. |
| FR-13: dashboard summary | Phase 6 | Counts by status match saved records. |
| FR-14: local persistence | Phase 4 | AT-08 and repository restart test. |
| FR-15: empty state | Phase 6 | AT-09; helpful action shown when no ideas exist. |
| FR-16: sorting | Phase 6 | Recently updated and priority ordering tests. |
| NFR-01, NFR-06: usability/accessibility | Phases 5–7 | Screen review, labels, readable text, clear status text. |
| NFR-02: performance | Phase 7 | 1,000-idea list/search check against proposed 2-second target. |
| NFR-03, NFR-09: reliability/data integrity | Phases 3–7 | Persistence, storage failure, and unique-ID update/delete tests. |
| NFR-04, NFR-05: privacy/security boundary | Phases 1 and 7 | Confirm local-only scope and absence of public URLs/external transmission. |